## Remarks
Stage Phase
0% | 3% | 7% | 10% | 14% | 17.17% | 20.67% | 24.17% | 27.67% | 31.17% | 34.67% | 38.17% | 41.67% | 45.17% | 48.67% | 52.17% | 55.67% | 59.17% | 62.67% | 66.17% | 69.67% | 73.17% | 76.67% | 80.17% | 83.67% | 87.17% | 90.67%
Completed
0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95% | 100%
Stopped
0% | 12.5% | 25% | 37.5% | 50% | 62.5% | 75% | 87.5% | 100%
State
Non-Start | Abolition | Preparing | Prepared | To do | Being Start | In Progress | In Stop | Suspension | Cancel | Done | Follow-Up | Complete

## Overall
Date & Week | 20-5-2025 (week 1) | 21-5-2025 (week 1) | 22-5-2025 (week 1) | 23-5-2025 (week 1) | 24-5-2025 (week 1) | 25-5-2025 (week 1) | 26-5-2025 (week 1) | 27-5-2025 (week 2) | 28-5-2025 (week 2) | 29-5-2025 (week 2) | 30-5-2025 (week 2) | 31-5-2025 (week 2) | 1-6-2025 (week 2) | 2-6-2025 (week 2) | 3-6-2025 (week 3) | 4-6-2025 (week 3) | 5-6-2025 (week 3) | 6-6-2025 (week 3)
Work Phases & Time
Project Preparing I：Bring storming Time： ~ 2 hrs | COMPLETED
Project Preparing II：Mindmap Time： ~ 2 hrs | COMPLETED
Project Preparing III：Create a Theme Time： ~ 2 hrs | COMPLETED
Project Preparing IV：Defind a goal Time： ~ 2 hrs | COMPLETED
Project Preparing V： Required Resources Time： ~ 2 hrs | COMPLETED
Write a draft project proposal Time：2 hrs | Completee 50% | Complete 62.5% | Complete 65% | ＳＴＯＰＥＤ | COMPLETED
Editing I：Revise the draft proposal Time：1 hrs |  |  |  |  | COMPLETED
Write a simple project poposal Time：2hrs 10mins |  |  |  |  | COMPLETED
Get ready I：Create a work table Time：45 mins | [5 empty] | ＳＴＯＰＥＤ | ＳＴＯＰＥＤ | COMPLETED
Resarching I：Intergrate APIs (Timer) Time：1hrs 10mins | [8 empty] | ＤＯＮＥ |  | COMPLETED
Resarch II：Intergrate APIs (Security) Time：40 mins | [8 empty] | Complete 10% | ＤＯＮＥ | COMPLETED
Resarch III；Intergrate APIs (Date) Time：40 mins | [8 empty] | ＳＴＯＰＥＤ | Follow Up | COMPLETED
Write a Resarch Memorandum (I) Time：2 hrs 15 mins | [8 empty] | ＳＴＯＰＥＤ | Complete 25% | COMPLETED
Updating I：Update work-table (1) Time：15 mins | [8 empty] | COMPLETED
Updating II：Update work-table (2) Time：10 mins | [9 empty] | COMPLETED
Write a hand darft pseudocode (I) Time：~5 mins | [10 empty] | Complete 2% | COMPLETED
Updating III：Update work-table (3) Time：8 mins | [10 empty] | COMPLETED
Testing I：Test pseudocode(I) Time：30 mins | [11 empty] | COMPLETED
Editing II：Revise pseudocode (I) Time：5 mnis | [11 empty] | ＤＯＮＥ | COMPLETED
Testing II：Test revised pseudocode(I) Time：30 mins | [11 empty] | ＤＯＮＥ | Follow Up | COMPLETED
Updating IV：Update work-table (4) Time：7 mins | [11 empty] | COMPLETED
Editing II：Revise pseudocode (II) Time：10 mnis | [12 empty] | ＤＯＮＥ | COMPLETED
Testing II：Test revised pseudocode (II) Time：46 mnis | [12 empty] | ＤＯＮＥ | Follow Up | COMPLETED
Updating V：Update work-table (5) Time：10 mins | [12 empty] | COMPLETED
Write a code hand darft(I)：Pseudocode(1) ｜Time：25 mins | [12 empty] | ＳＴＯＰＥＤ | ＳＴＯＰＥＤ | ＤＯＮＥ
Updating VI：Update work-table (6) Time：5 mins | [13 empty] | COMPLETED
Updating VII：Update work-table (7) Time：5 mins | [14 empty] | COMPLETED
Testing III：Test code hand darft (1) Time：5 mins | [15 empty] | Complete 80% | COMPLETED
Updating VIII：Update work-table (8) Time：5 mins | [15 empty] | COMPLETED
Write a Resarch Memorandum (2) Time：20 mins | [16 empty] | ＳＴＯＰＥＤ | COMPLETED
Developing I：Develop the prototype Time：30 mins | [16 empty] | ＳＴＯＰＥＤ | COMPLETED
Updating IX：Update work-table (9) Time：10 mins | [16 empty] | ＳＴＯＰＥＤ | COMPLETED
Follow-Up Work | [17 empty] | COMPLETED

## 工作表2
33 | phases
18 | days
2.5714 | weeks